## Sheet1
Product ID | Product Name | Date Identified | Failure Description | Possible Causes | Features Impacted | Severity (Low/Medium/High) | Status (Open/Resolved/Closed) | Corrective Actions | Date of Resolution | Responsible Person | Comments
P001 | Widget A | 2024-09-01 | Battery failure leading to sudden shutdown | Poor battery quality, Overheating | Battery, Power Supply | High | Open | Replace battery supplier, Improve thermal management |  | John Doe | Needs urgent attention
P002 | Gadget B | 2024-09-10 | Software crash during startup | Bug in firmware, Incompatible software update | Software, Firmware | Medium | Resolved | Update firmware, Test compatibility | 2024-09-12 | Jane Smith | Issue resolved, no further action needed
P003 | Appliance C | 2024-09-15 | Water leakage from internal component | Faulty seal, Poor design of water compartment | Seal, Water compartment | High | Open | Redesign seal, Inspect design |  | Alice Brown | Potential safety hazard
P004 | Tool D | 2024-09-12 | Excessive noise during operation | Worn-out bearings, Loose parts | Bearings, Motor | Low | Closed | Replaced bearings, Tightened components | 2024-09-13 | Bob White | Regular maintenance scheduled